## Sheet1
UNIVERSITY OF NORTHERN IOWA
Budget Planning Steps - Summary |  |  | DRAFT
Month | Step | Dates | Planning Steps
AUGUST | 1 |  | Senior Leadership Team begins budget planning discussions
| 2 | August 16 | Next FY Appropriation Request finalized for submission to Board
| 3 | August 16 | Next FY Capital Appropriation Request for submission to Board
| 4 |  | Budget Advisory Committee current year discussion
SEPTEMBER | 5 | September 15 | Budget Request & Prioritization Process initiated with form and instructions forwarded to Divisions/Department
| 6 |  | Senior Leadership Team reviews/revises plan of current fiscal year with institutional priorities (updated monthly)
OCTOBER | 7 | October 13 | Legislative Fiscal Committee presentation
NOVEMBER | 8 |  | Continue budget topic discussions with Faculty Senate and P&S Council (continues through year)
| 9 |  | Budget Advisory Committee Meeting
DECEMBER | 10 |  | Governor conducts budget hearings
| 11 | December 15 | Preliminary fringe benefit rates calculated
| 12 | December 31 | Divisions complete program review with recommendations
JANUARY | 13 | January 11 | Governor's Office completes budget hearings and formulates recommendations/scenarios updated with Governor's budget
| 14 | January 12 | Legislature convenes/reply to legislative requests and comment on legislation
| 15 | January 25 | Residence comprehensive budget report due to Board
| 15 |  | Planning scenarios are developed based on Governor's recommendation
| 16 | January 31 | Budget Request & Prioritization Process forms due to Budget
FEBRUARY | 17 | Febraury 7 | Preliminary enrollment projections
| 18 |  | Budget Advisory Committee Meeting
| 19 |  | Provost & Senior VP Initiate budget discussions with Faculty Senate and P&S Council
| 20 | February 15 | Senior Leadership Team Vet new Tuition Rate Proposal
| 21 | February 15 | Senior Leadership Team Vet new and revised Mandatory Fee Proposals
| 22 | February 28 | Senior Leadership Team approves which Budget Requests will be included for budget planning
MARCH | 23 | March 10 | President and Senior Vice President share 'near final' draft of budget decisions to Budget Advisory Committee and Faculty Leadership
| 24 | March 15 | Submit Proposed Tuition and Mandatory Fee requests to Board
| 25 | March 15 | Apply results of bargaining agreements to budget scenarios
| 26 | March 20 | Request final feedback from Faculty Senate and P&S Council on budget plan
APRIL | 27 | April 9 | Distribute Self-Support Funds Budget Worksheets to all divisions/departments
| 28 | April 14-15 | Board first reading proposed tuition and mandatory fees
| 29 | April 14-15 | Salary policy for all employee groups presented to the Board
MAY | 30 | May 6-11 | Distribute Salary Increase Worksheets
| 31 | May 14 | Self-Support Fund Worksheet budgets due
| 32 | May 15 | Final proposed budget determined by President based on Legislative appropriations and Governor's action
| 33 | May 28 | Salary Increase Worksheets due
JUNE | 34 | June 1-3 | Board approval of Tuition and Mandatory Fees
| 35 | June 10 | Allocate new resources and reallocate existing resources per approved plan
| 36 | June 28 | Budget submitted to Board
| 37 | June 30 | Communicate final approved budget to University community